## Project Summary
Project Name : | Majorda Villa |  |  | PROJECT SUMMARY
Client : | Mr. Sanjay Rao
Date : | 2026-01-04
CODE | Description | Budget | WO Value | % Progress | Payment Value
CIV | Civil Works | 15000000 | 10107425.95 | 51% | 1535000
PLB | Plumbing Works |  | 0 | 0% | 0
ELC | Electrical Works |  | 13530 | 100% | 13530
DWG | Doors, Windows & Glazing |  | 0 | 0% | 0
SWP | Swimming Pool Works |  | 0 | 0% | 0
HVC | HVAC / Air Conditioning |  | 0 | 0% | 0
FIN | Finishing Works |  | 0 | 0% | 0
LAN | Landscapping & External Works |  | 0 | 0% | 0
FAB | Metal & Steel Fabrication |  | 0 | 0% | 0
CSA | Client Supplied Assets |  | 0 | 0% | 0
PRF | Professional Fees |  | 14000 | 100% | 296520
STC | Approvals & Statutory Charges |  | 0 | 0% | 0
PTC | Petty Cash / Running Expenses |  | 0 | 0% | 0
CON | Contingency |  | 0 | 0% | 0

## 01-Task List
Project Name : | Majorda Villa |  | PROJECT TASK LIST
Client : | Mr. Sanjay Rao
Date : | 2026-03-23
Sr No | OPEN Task Description | Action By | Deadline | Status / Notes
1 | SWall beam to be included in render. | Omkar/Rajesh | 2026-03-27
2 | Column or stubbed steel on NW side got floating roof to be in rcc clarity. | Omkar/Rajesh | 2026-03-27
3 | Jali wall material? | Omkar/Rajesh | 2026-03-27
4 | Ventilator on seast room bay window in the east-facing room. (Suggestion if this is doable and look good) | Omkar/Rajesh | 2026-03-27
5 | Cantilever extension to 4 ft into the setback to be checked with PMC. | Amit | 2026-03-27 | Pls provide with section drawing to highlight this area, will check onsite and revert.
6 | Shingles and material on the roof for render and south-side solar panels. | Omkar/Rajesh | 2026-03-27
7 | POV for Terrace fireplace. | Omkar/Rajesh | 2026-03-27
8 | south side FF opening for rooms does not match with the floor plan. ( Need some clarity) | Omkar/Rajesh | 2026-03-27
9 | NW room sky roof POV. | Omkar/Rajesh | 2026-03-27
10 | Laterite vs. terracotta brick cladding material mix. | Omkar/Rajesh | 2026-03-27
11 | Can we obtain specific massing or design details for the entrance door, if possible? | Omkar/Rajesh | 2026-03-27
12 | Installing CCTV Cameras onsite | Amit | 2026-03-25
13 | Swimming Pool services drawings to be issued. | Santosh | 2026-03-25
14 | Pool Vendor onboarding | Amit | 2026-03-30 | After confirmation of swimming pool services drawings
15 | Electrical Specs/BOQ to be issued | MEP | 2026-03-30
16 | Electrican Vendor Onboarding | Amit | 2026-04-10 | After receipt of Electrical BOQ
17 | Plumbing Specs/BOQ to be Issued | MEP | 2026-03-30
18 | Plumbing Vendor Onboarding | Amit | 2026-04-10 | After receipt of Plumbing BOQ
19 | Door Window Schedule to be issued | Omkar/Rajesh | 2026-03-30
20 | Car Park area Entry from North East, clashing with onsite electrical post, need final decision to move forward | Omkar/Rajesh | 2026-03-30
Sr No | COMPLETED Task Description | Action By | Deadline | Status / Notes
1 | E-mail Confirmation to Structural | Omkar / Rajesh | 2025-01-05 | Critical, to be completed
2 | Footing & Steel Drawings | Paresh | 2026-03-31 | Mamta will take 3 days to complete steel & footing drawings if no changes.
3 | Civil BOQ | Amit | 2026-04-04 | Contract ready BOQ will only be ready after receipt of complete structural drawings including footing & steel
4 | Civil Contract Award, Advance to be paid | Amit | 2026-04-07 | PS Engrs, SS Construction, Madhav Patra (Team available for mid Jan)
5 | Civil Works to be started onsite | Amit | 2026-04-10 | Vendor to be confirmed.
6 | MEP Meeting for Levels, Septic & Sump Location | Amit | 2026-04-01 | After receipt of Footing drawings.
7 | MEP BOQ & Specs to be prepared | MEP Consultant | 2026-04-06 | Needed once we reach plinth filling.
8 | Electrical Contract Award, Advance to be paid | Amit | 2026-04-12 | Electrical contractor to be onboard before plinth filling.
Formulas:
PROJECT TASK LIST = [PROJECT TASK LIST, row above]+4

## 02-Weekly Progress Report
Project Name : | Majorda Villa |  |  |  |  | PROJECT PROGRESS REPORT
Client : | Mr. Sanjay Rao
Date : | 2026-01-04
CODE | Vendor | WO Refn | WO Issued Date | Start Date | End Date | % Completed | Comments | CODE |  | Average Value
CIV | SS Construction | TAC_WO_25_003 | 2025-12-12 | 2025-12-14 | 2025-12-20 | 100% | Activity Completed | CIV | Civil Works | 51%
ELC | Suraj Electrician | TAC_WO_25_004 | 2025-12-23 | 2025-12-23 | 2025-12-28 | 100% | Activity Completed | PLB | Plumbing Works | 0%
CIV | Rajesh Construction | TAC_WO_25_005 | 2026-02-07 | 2026-02-17 | 2026-12-15 | 2% |  | ELC | Electrical Works | 100%
PRF | CDSP Global | TAC_WO_25_006 | 2026-03-01 | 2026-02-18 | 2026-02-18 | 100% | Activity Completed | DWG | Doors, Windows & Glazing | 0%
[8 empty] | SWP | Swimming Pool Works | 0%
[8 empty] | HVC | HVAC / Air Conditioning | 0%
[8 empty] | FIN | Finishing Works | 0%
[8 empty] | LAN | Landscapping & External Works | 0%
[8 empty] | FAB | Metal & Steel Fabrication | 0%
[8 empty] | CSA | Client Supplied Assets | 0%
[8 empty] | PRF | Professional Fees | 100%
[8 empty] | STC | Approvals & Statutory Charges | 0%
[8 empty] | PTC | Petty Cash / Running Expenses | 0%
[8 empty] | CON | Contingency | 0%

## 03-Work Order Tracker
Project Name : | Majorda Villa |  |  |  |  | WORK ORDER TRACKER
Client : | Mr. Sanjay Rao
Date : | 2026-01-04
CODE | Vendor | WO Refn | WO Issued Date | WO Value | GST | Retention Value | Start Date | End Date | CODE |  | Total Value
CIV | SS Construction | TAC_WO_25_003 | 2025-12-12 | 35000 | 0 | 0 | 2025-12-14 | 2025-12-20 | CIV | Civil Works | 10107425.95
ELC | Suraj Electrician | TAC_WO_25_004 | 2025-12-23 | 13530 | 0 | 0 | 2025-12-23 | 2025-12-28 | PLB | Plumbing Works | 0
CIV | Rajesh Construction | TAC_WO_25_005 | 2026-02-07 | 10072425.95 | 1813036.671 | 503621.2975 | 2026-02-17 | 2026-12-15 | ELC | Electrical Works | 13530
PRF | CDSP Global | TAC_WO_25_006 | 2026-03-01 | 14000 | 2520 | 0 | 2026-02-18 | 2026-02-18 | DWG | Doors, Windows & Glazing | 0
[9 empty] | SWP | Swimming Pool Works | 0
[9 empty] | HVC | HVAC / Air Conditioning | 0
[9 empty] | FIN | Finishing Works | 0
[9 empty] | LAN | Landscapping & External Works | 0
[9 empty] | FAB | Metal & Steel Fabrication | 0
[9 empty] | CSA | Client Supplied Assets | 0
[9 empty] | PRF | Professional Fees | 14000
[9 empty] | STC | Approvals & Statutory Charges | 0
[9 empty] | PTC | Petty Cash / Running Expenses | 0
[9 empty] | CON | Contingency | 0
Total: |  |  |  | 10134955.95 |  | 503621.2975

## 04-Payment Certificate Tracker
Project Name : | Majorda Villa |  |  |  | PROJECT CASHFLOW TRACKER
Client : | Mr. Sanjay Rao
Date : | 2026-01-04
CODE | Vendor | PC Refn | PC Date | PC Value | Payment Value | Payment Date | CODE |  | Total Value
CIV | SS Construction | TAC_PC_25_003 | 2026-01-04 | 35000 | 35000 | 2025-12-30 | CIV | Civil Works | 1535000
ELC | Suraj Electrician | TAC_PC_25_004 | 2025-12-28 | 13530 | 13530 | 2025-12-30 | PLB | Plumbing Works | 0
PRF | Third Angle Concepts | TAC_PC_25_005 | 2025-12-28 | 140000 | 140000 |  | ELC | Electrical Works | 13530
PRF | CDSP Global | TAC_PC_25_006 | 2026-03-01 | 16520 |  |  | DWG | Doors, Windows & Glazing | 0
CIV | Rajesh Construction | TAC_PC_25_007 | 2026-03-01 | 1500000 |  |  | SWP | Swimming Pool Works | 0
PRF | Third Angle Concepts | TAC_PC_25_008 | 2026-03-09 | 140000 |  |  | HVC | HVAC / Air Conditioning | 0
[7 empty] | FIN | Finishing Works | 0
[7 empty] | LAN | Landscapping & External Works | 0
[7 empty] | FAB | Metal & Steel Fabrication | 0
[7 empty] | CSA | Client Supplied Assets | 0
[7 empty] | PRF | Professional Fees | 296520
[7 empty] | STC | Approvals & Statutory Charges | 0
[7 empty] | PTC | Petty Cash / Running Expenses | 0
[7 empty] | CON | Contingency | 0
Total: |  |  |  |  | 188530
Formulas:
Payment Date = [Payment Date, row above]

## 05-PMC Commercials
Project Name : | Majorda Villa |  |  |  | PMC COMMERCIALS
Client : | Mr. Sanjay Rao
Date : | 2026-01-04
PMC Retainer/Month : | 140000
PC Issue Date | PC Refn | Payment Date | Description | Amount | TDS | Amount Received
0 | 0 | 2025-11-01 | 50% Advance Dec-25 | 70000 | 7000 | 63000
2025-12-28 | TAC_PC_25_005 |  | 50% Bal Dec-25 + 50% Adv Jan -26 | 140000
Total: |  |  |  |  | 7000

## 06-Petty Cash Tracker
Project Name : | Majorda Villa | PETTY CASH REGISTER
Client : | Mr. Sanjay Rao
Date : | 2026-01-04
Total Received: | 25000
Total Expenses: | 81300
Balance Available : | -56300
Date | Description | Amount | Bill / Invoice
2025-12-09 | Received from Mr. Sanjay | 25000
2025-12-10 | Received from Mr. Sanjay | 60000
2025-12-14 | Assistant Engr (Unofficial) | -45000
2025-12-14 | File Procession (Unofficial) | -15000
2025-12-26 | Lineman (Unofficial) | -15000
2025-12-26 | Meter Box | -3800 | Tax Invoice
2025-12-12 | Electricity Connection Fees | -2500 | Pending
2025-12-16 | File Procession (Unofficial) | -15000 | Cash
2025-12-16 | Assistant Engr (Unofficial) | -40000 | Cash
2025-12-26 | Meter Box | -3800 | Tax Invoice
2025-12-26 | UG Cabling (Unofficial) | -20000 | Cash

## 07-CSA
Project Name : | Majorda Villa |  | ASSET MANAGEMENT REGISTER
Client : | Mr. Sanjay Rao
Date :
CODE | WO Refn | Description | Value | Received Date
CSA

## Code-Categories
| CODE | Category | Inclusion | Exclusion to CSA (Client Supplied Appliances)
1 | CIV | Civil Works | Excavation, RCC, PCC, masonry, plastering, waterproofing, compound wall, all Grey Works
2 | PLB | Plumbing Works | Piping, valves, traps, drainage, pump-room piping, STP Setup, Chambers, Storm Drain, Geyser Piping and Fixing of final sanitaryware, steam, sauna, jacuzzi, geyser fixtures | Sanitaryware, faucets, shower sets, pumps.
3 | ELC | Electrical Works | Conduits, wiring, DBs, breakers, earthing, CCTV, Home Automation, DG Setup, Invertor Setup, Internet Setup, Solar Works and Fixing of all type final fixtures. | Lights, fans, switches, chandeliers.
4 | DWG | Doors, Windows & Glazing | External Aluminum/UPVC, Main doors, skylights, facade glazing, External Envelope Closure. | Loose Furnitures, Special Lights
5 | SWP | Swimming Pool Works | Related to Swimming Pool, Waterproofing, Tiling, Pool Light Fixing, Complete Pool Plumbing & Electricals, Pumps, Heaters | AC indoor/outdoor units.
6 | HVC | HVAC / Air Conditioning | Copper piping, drain lines, insulation and fixing of final units internal and external. | Tile, Stone, Pavers, Roofing Tile, Decorative lights, mirrors, loose décor.
7 | FIN | Finishing Works | Internal Doors, Windows, Glazing, Flooring, Tiling, Painting (Int & Ext), False ceiling, Wardrobes, kitchen, vanities, fixed furniture. | Loose furniture (sofas, beds, dining).
8 | LAN | Landscapping & External Works | Greenscaping, Plants, turf, irrigation, pavers, decks. | Garden lights, outdoor furniture.
9 | FAB | Metal & Steel Fabrication | Railings, gate fabrication, structural framing for roofing, installation of roofing tiles, framing for jali walls, installation of jali wall, steel brackets, platforms, and structural steel elements. | Specialized ornamental items (if client-supplied).
9 | CSA | Client Supplied Assets | Sanitory Fixtures, light fixtures, HVAC Units, Pumps, DG Unit, all type of appliances, loose furniture, décor, Sofa, Bed, Table, Cabinet, Curtains, Rugs, Cushions, | CCTV cameras, smart locks, automation gadgets.
10 | PRF | Professional Fees | Architect, Engineers, Consultants, PMC, CA, Security Guards.
11 | STC | Approvals & Statutory Charges | Govt/Panchayat Permissions, licenses, NOCs, utility connections.
12 | PTC | Petty Cash / Running Expenses | Drinking Water, Water Tankers, Chairs, stationery, extension boards, Health compliant activities
13 | CON | Contingency | Buffer for variations & unforeseen items.

## Baseline Budget
Baseline Budget
|  |  |  | % | Budget
1 | CIV | Civil Works | Excavation, RCC, PCC, masonry, plastering, waterproofing, compound wall, all Grey Works | 21% | 15000000
2 | PLB | Plumbing Works | Piping, valves, traps, drainage, pump-room piping, STP Setup, Chambers, Storm Drain, Geyser Piping and Fixing of final sanitaryware, steam, sauna, jacuzzi, geyser fixtures | 7% | 5000000
3 | ELC | Electrical Works | Conduits, wiring, DBs, breakers, earthing, CCTV, Home Automation, DG Setup, Invertor Setup, Internet Setup, Solar Works and Fixing of all type final fixtures. | 7% | 5000000
4 | DWG | Doors, Windows & Glazing | External Aluminum/UPVC, Main doors, skylights, facade glazing, External Envelope Closure. | 11 | 8000000
5 | SWP | Swimming Pool Works | Related to Swimming Pool, Waterproofing, Tiling, Pool Light Fixing, Complete Pool Plumbing & Electricals, Pumps, Heaters | 2% | 1200000
6 | HVC | HVAC / Air Conditioning | Copper piping, drain lines, insulation and fixing of final units internal and external. | 4% | 3000000
7 | FIN | Finishing Works | Internal Doors, Windows, Glazing, Flooring, Tiling, Painting (Int & Ext), False ceiling, Wardrobes, kitchen, vanities, fixed furniture. | 17% | 12000000
8 | LAN | Landscapping & External Works | Greenscaping, Plants, turf, irrigation, pavers, decks. | 3% | 2000000
9 | CSA | Client Supplied Assets | Sanitory Fixtures, light fixtures, HVAC Units, Pumps, DG Unit, all type of appliances, loose furniture, décor, Sofa, Bed, Table, Cabinet, Curtains, Rugs, Cushions, | 11% | 8000000
10 | PRF | Professional Fees | Architect, Engineers, Consultants, PMC, CA, Security Guards. | 7% | 5000000
11 | STC | Approvals & Statutory Charges | Govt/Panchayat Permissions, licenses, NOCs, utility connections. | 2% | 1200000
12 | PTC | Petty Cash / Running Expenses | Drinking Water, Water Tankers, Chairs, stationery, extension boards, Health compliant activities | 3% | 1800000
13 | CON | Contingency | Buffer for variations & unforeseen items. | 4% | 2800000
70000000
| Code | Budget
| CIV | 15000000
| PLB | 5000000
| ELC | 5000000
| DWG | 8000000
| SWP | 1200000
| HVC | 3000000
| FIN | 12000000
| LAN | 2000000
| CSA | 8000000
| PRF | 5000000
| STC | 1200000
| PTC | 1800000
| CON | 2800000