## Project Summary
Project Name : | Majorda Villa
Client : | Mr. Sanjay Rao
Date :
CODE | Description | WO Value | % Progress | Payment Value | Deadline | Difference
CIV | Civil Works | 8000000 | 20% | 200000
PLB | Plumbing Works | 3000000 | 30% | 200000
ELC | Electrical Works | 3000000 | 10% | 200000
SWP | Swimming Pool Works | 1000000 | 5% | 200000
HVC | HVAC / Air Conditioning | 850000 | 30% | 200000
FIN | Finishing Works | 6000000 | 25% | 200000
CRP | Carpentry / Fixed | 1500000 | 10% | 200000
LAN | Landscapping & External Works | 600000 | 50% | 200000
EQP | Equipments & Special System | 6000000 | 100% | 200000
PRF | Professional Fees | 6000000 | 5% | 200000
STC | Approvals & Statutory Charges | 8000000 | 80% | 200000
OVH | Site Overheads / Running Expenses | 5000000 | 60% | 200000
CSA | Client Supplied Assets | 8000000 | 75% | 200000
CON | Contingency | 2500000 | 30% | 200000

## Weekly Progress Report
Project Name : | Majorda Villa |  | PROJECT PROGRESS REPORT
Client : | Mr. Sanjay Rao
Date :
CODE | WO Refn | Vendor | % Completed | Comments | CODE | Average Value
CIV |  |  | 20% |  | CIV | 20%
PLB |  |  | 30% |  | PLB | 30%
ELC |  |  | 10% |  | ELC | 10%
SWP |  |  | 5% |  | SWP | 5%
HVC |  |  | 30% |  | HVC | 30%
FIN |  |  | 25% |  | FIN | 25%
CRP |  |  | 10% |  | CRP | 10%
LAN |  |  | 50% |  | LAN | 50%
EQP |  |  | 100% |  | EQP | 100%
PRF |  |  | 5% |  | PRF | 5%
STC |  |  | 80% |  | STC | 80%
OVH |  |  | 60% |  | OVH | 60%
CSA |  |  | 75% |  | CSA | 75%
CON |  |  | 30% |  | CON | 30%

## Work Order Tracker
Project Name : | Majorda Villa |  |  |  | PROJECT BUDGET TRACKER
Client : | Mr. Sanjay Rao
Date :
CODE | WO Refn | Vendor | WO Value | Retention Value | Start Date | End Date | CODE | Total Value
CIV | TAC_WO_25_001 | ABC | 8000000 | 400000 |  |  | CIV | 8000000
PLB |  |  | 3000000 | 150000 |  |  | PLB | 3000000
ELC |  |  | 3000000 | 150000 |  |  | ELC | 3000000
SWP |  |  | 1000000 | 50000 |  |  | SWP | 1000000
HVC |  |  | 850000 | 42500 |  |  | HVC | 850000
FIN |  |  | 6000000 | 300000 |  |  | FIN | 6000000
CRP |  |  | 1500000 | 75000 |  |  | CRP | 1500000
LAN |  |  | 600000 | 30000 |  |  | LAN | 600000
EQP |  |  | 6000000 | 300000 |  |  | EQP | 6000000
PRF |  |  | 6000000 | 300000 |  |  | PRF | 6000000
STC |  |  | 8000000 | 400000 |  |  | STC | 8000000
OVH |  |  | 5000000 | 250000 |  |  | OVH | 5000000
CSA |  |  | 8000000 | 400000 |  |  | CSA | 8000000
CON |  |  | 2500000 | 125000 |  |  | CON | 2500000
Total: |  |  | 59450000 | 2972500

## Payment Certificate Tracker
Project Name : | Majorda Villa |  |  |  | PROJECT CASHFLOW TRACKER
Client : | Mr. Sanjay Rao
Date :
CODE | PC Refn | Vendor | PC Value | PC Date | Payment Value | Payment Date | CODE | Total Value
CIV | TAC_PC_25_001 | ABC | 200000 |  | 200000 |  | CIV | 200000
PLB |  |  | 200000 |  | 200000 |  | PLB | 200000
ELC |  |  | 200000 |  | 200000 |  | ELC | 200000
SWP |  |  | 200000 |  | 200000 |  | SWP | 200000
HVC |  |  | 200000 |  | 200000 |  | HVC | 200000
FIN |  |  | 200000 |  | 200000 |  | FIN | 200000
CRP |  |  | 200000 |  | 200000 |  | CRP | 200000
LAN |  |  | 200000 |  | 200000 |  | LAN | 200000
EQP |  |  | 200000 |  | 200000 |  | EQP | 200000
PRF |  |  | 200000 |  | 200000 |  | PRF | 200000
STC |  |  | 200000 |  | 200000 |  | STC | 200000
OVH |  |  | 200000 |  | 200000 |  | OVH | 200000
CSA |  |  | 200000 |  | 200000 |  | CSA | 200000
CON |  |  | 200000 |  | 200000 |  | CON | 200000
Total: |  |  | 2800000 |  | 2800000

## Code-Categories
| CODE | Category | Inclusion | Exclusion to CSA (Client Supplied Appliances)
1 | CIV | Civil Works | Excavation, RCC, PCC, masonry, plaster, waterproofing, basic structure.
2 | PLB | Plumbing Works | Piping, valves, traps, drainage, pump-room piping. | Sanitaryware, faucets, shower sets, pumps.
3 | ELC | Electrical Works | Conduits, wiring, DBs, breakers, earthing | Lights, fans, switches, chandeliers.
4 | SWP | Swimming Pool Works | Waterproofing, Tiling, Pool Light Fixing, Complete Pool Plumbing & Electricals, Pumps, Heaters | Loose Furnitures, Special Lights
5 | HVC | HVAC / Air Conditioning | Copper piping, drain lines, insulation, installation. | AC indoor/outdoor units.
6 | FIN | Finishing Works | Doors, Windows, Glazing, Flooring, Tiling, Painting, False ceiling. | Tile, Stone, Pavers, Roofing Tile, Decorative lights, mirrors, loose décor.
7 | CRP | Carpentry / Fixed | Wardrobes, kitchen, vanities, fixed furniture. | Loose furniture (sofas, beds, dining).
8 | LAN | Landscapping & External Works | Plants, turf, irrigation, pavers, decks. | Garden lights, outdoor furniture.
9 | EQP | Equipments & Special System | Solar, filtration, STP, CCTV backbone. | CCTV cameras, smart locks, automation gadgets.
10 | PRF | Professional Fees | Architect, Engineers, Consultants, PMC, CA, Security Guards.
11 | STC | Approvals & Statutory Charges | Govt/Panchayat Permissions, licenses, NOCs, utility connections.
12 | OVH | Site Overheads / Running Expenses | Drinking Water, Water Tankers, Chairs, stationery, extension boards, Health compliant activities
13 | CSA | Client Supplied Assets | Fixtures, lights, appliances, loose furniture, décor.
14 | CON | Contingency | Buffer for variations & unforeseen items.

## CSA
Project Name : | Majorda Villa
Client : | Mr. Sanjay Rao
Date :
CODE | WO Refn | Description | Qty | Received Date
CSA

## Petty Cash Tracker
Project Name : | Majorda Villa
Client : | Mr. Sanjay Rao
Date :
Date | PC Refn | PC Value | Bill / Invoice

## PC
Contractor |  |  | PAYMENT CERTIFICATE
|  |  | PC Refn: |  | TAC_PC_25_001
PC Date:
GST No : |  |  | WO Refn:
Sr. No. | Scope of Work | Rate | Qty | Unit | Total
PMC Comments |  |  | Sub Total : |  | 0
|  |  | Retention 5% : |  | 0
|  |  | Total : |  | 0
|  |  | CGST : |  | 0
|  |  | SGST : |  | 0
|  |  | Grand Total : |  | 0

## WO
Axion Connect Infosolutions Pvt Ltd |  | WORK ORDER
DSR Elite, No 109
Mahadevpura - Bangaluru |  | WO Refn: | TAC_WO_025_001
Karnataka - 560048 |  | WO Date:
|  | CODE : | CIV
GST No : |  | ISSUED BY: | Third Angle Concepts (PMC)
To, |  | Shipping to
Plot No- 51/16, Beach Road
Panchecho Waddo, Betalbatim
Majorda - Goa, 403713
Contact: | Mr. ABC | Mr. Amit Chinchuwar
Mobile: |  | 7387471134
Sr No. | Description | Quantity | Rate | Total
Notes & Payment Terms |  | Subtotal :
5% Retention applicable on all PC (Ref 16) |  | Discount:
Total :
CGST :
SGST :
Grand Total :
Timeline |  | Warranty
Start Date: |  | Product :
End Date: |  | Workmenship : |  | 12 Months
General Terms and Condition:
1 | The Contractor shall ensure all labour, technicians and supervisors possess valid police verification documents, health cards and mandatory statutory clearances, available at all times during their engagement.
2 | The Contractor is fully responsible for safety of their workforce and must provide PPE such as safety shoes, helmets, belts, gloves and goggles.
3 | Any accident, injury or fatality shall be handled entirely by the Contractor including medical treatment, compensation and legal liability.
4 | Waste must be segregated, disposed safely and without burning or chemical dumping. Dust control and tidy operations must be maintained at all times.
5 | Contractor shall maintain daily site cleanliness. All debris or waste shall be stored at a designated area and cleared regularly to prevent obstruction to other works or safety hazards.
6 | Works must be executed strictly as per approved drawings, materials and specifications within stipulated timelines.
7 | Contractor is responsible for safe storage and protection of all materials (client-supplied or contractor-supplied). Any losses or damages due to improper handling will be recovered from the Contractor.
8 | All work shall follow approved site working hours. High-noise or disruptive tasks shall require 24-hour prior intimation to PMC.
9 | All PMC observations and instructions will be issued only to the Contractor’s designated site supervisor. No direct instruction will be given to labour.
10 | Any snags or defects identified by PMC must be rectified within the stipulated period. Failure to do so will result in corrective work being executed through alternate agencies at Contractor’s cost.
11 | Standard workmanship warranty of 12 Months from the date of Handover applicable to the Contractor’s. Any failure within the defects liability period shall be rectified without cost.
12 | Any increase or decrease in quantities or scope must be informed to PMC immediately. Revised Work Orders or Change Orders will be issued accordingly. Work executed without prior written approval will not be considered.
13 | Payment Certificates will be prepared by PMC based on joint measurements. Contractor must provide complete measurement sheets and ensure supervisor presence during inspections.
14 | All payments shall be released strictly against PMC-approved and signed Payment Certificates.
15 | Payment Certificates shall be prepared between the 25th and 30th of each month. Submissions outside this window will move to the next cycle.
16 | A 5% retention will be deducted from all payments. Retention will be released only after full completion of work and after a minimum three-month period post-monsoon, subject to no defects.
17 | Contractor personnel shall not share site photos, drawings, videos or project details on social media or externally without written approval from the Company/PMC.
18 | In case of breach of any clause or non-performance, the Company reserves the right to execute the works through alternate agencies. Any cost or time impact arising from such action will be fully recovered from the Contractor’s payments or retention.
Accepted and Agreed
Mr. ABC